## Slide 1: Poornima Institute of Engineering & Technology
Smart Parking System
TEAM NAME: The Brogrammers
PROJECT ID: 8CS PR 2018_19_30
STUDENTS NAME:
1. Aniket Mathur
2. Kartik Tiwari
3. Mahesh Meena
Project Guide By: Dr. Praveen Gupta Department of Computer Engineering PIET , Jaipur

## Slide 2: Vision of Department
Department of computer engineering shall create an environment in which new ideas, research and technology grows and form which technocrats and innovators of tomorrow come forward to face the global challenges. It aims at being recognized globally as role model and be a part of substantial natural resources.

## Slide 3: Mission of Department
To develop competent professional with innovative mind set, problem solving, design and implementation skills through excellent under graduate education.
To provide platform to students so that they can expertise themselves as a computer professional, entrepreneurs or as a manager while fulfilling their ethical and social responsibility in a globally competitive environment.
To contribute significantly to the research and discovery of new arenas of methods and knowledge in the field of computer engineering.

## Slide 4: Index
Introduction
Product Backlog
Sprint Backlog-1
Sprint Backlog-II
Sprint Backlog-III
Sprint Backlog-IV
Results
Conclusion and Future Scope

## Slide 5: Introduction
Smart Parking System will enable users to see whether parking is available in a parking lot on not.
Parking Areas will be created by the Parking Owner and users can see the Parking Availability.
Web Portal will be there and users are not allowed to Login.

## Slide 6
Product Backlog
PRODUCT BACKLOG |  |  |  |  |  |  |  | 
 |  |  | Batch 2018_2019 |  |  |  |  | 
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
 |  | AS A/AN | I WANT TO | SO THAT |  |  |  | 
1 | SB1/US1 | Admin | open web portal | admin can register free parking lots. | 1 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US2 | Admin | Registers Himself/Herself | parking lot can be verified | 2 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US3 | Admin | sign's in | admin puts his/her parking lot | 3 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US4 | Admin | will register only single parking lot | each admin is associated with one parking lot | 1 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US5 | Admin | will keep record of vehicles | no vehicle is stolen | 2 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US6 | Admin | mention the number of spaces available | user can park vehicles. | 2 | Kartik Tiwari | 22-09-2018 | 
1 | SB1/US7 | Admin | mention the time period of availability of spaces | parking problems will be reduced. | 1 | Kartik Tiwari | 29-09-2018 | 
1 | SB1/US8 | Admin | control incoming vehicles | number of spaces will decrease. | 2 | Kartik Tiwari | 29-09-2018 | 
1 | SB1/US9 | Admin | control outgoing vehicles | number of spaces will increase | 2 | Kartik Tiwari | 29-09-2018 | 
1 | SB1/US10 | Admin | register only free parking lots | user can park their vehicles. | 1 | Kartik Tiwari | 29-09-2018 | 
1 | SB1/US11 | Admin | cover all the parking lots | parking problems will reduce in that area. | 1 | Kartik Tiwari | 02-10-2018 | 
1 | SB1/US12 | Admin | predict the available parkings | I can interact with the tools of application. | 1 | Kartik Tiwari | 02-10-2018 | 
1 | SB1/US13 | Admin | change the number of spaces automatically | user can see available spaces. | 1 | Kartik Tiwari | 02-10-2018 | 
2 | SB2/US1 | Admin | display message if the parking is available | user can look for another parking. | 4 | Kartik Tiwari | 02-10-2018 | 
2 | SB2/US2 | Admin | display all the nearby parking lots | user can choose his/her suitable parking. | 4 | Kartik Tiwari | 02-10-2018 | 
2 | SB2/US3 | Admin | paid parking has different criteria | admin will not include paid parking. | 5 | Kartik Tiwari | 09-10-2018 | 
2 | SB2/US4 | User | open web portal | enter particular area | 1 | Kartik Tiwari | 09-10-2018 | 
2 | SB2/US5 | User | display the parking lots | user can click on a particular parking slot. | 1 | Kartik Tiwari | 09-10-2018 | 
2 | SB2/US6 | User | if parking is available | it will show how many spaces are available. | 1 | Kartik Tiwari | 09-Oct-18 | 
2 | SB2/US7 | User | is free to see parking availability | no charges will be there | 1 | Kartik Tiwari | 16-Oct-18 | 
2 | SB2/US8 | User | is free to see parking availability anytime | no time boundations will be there | 1 | Kartik Tiwari | 16-Oct-18 | 
2 | SB2/US9 | User | can see Parking with normal Internet Connection | No Fast Internet will be needed | 1 | Kartik Tiwari | 16-Oct-18 | 
2 | SB2/US10 | User | prediction of two wheelers | will be shown separate for two wheelers | 2 | Kartik Tiwari | 16-Oct-18 | 
2 | SB2/US11 | User | prediction of three wheelers | will be shown separate for three wheelers | 5 | Kartik Tiwari | 16-Oct-18 | 
2 | SB2/US12 | User | prediction of four wheelers | will be shown separate for four wheelers | 4 | Kartik Tiwari | 23-Oct-18 | 
2 | SB2/US13 | User | it will predict that | till when the parking will be available. | 4 | Kartik Tiwari | 23-Oct-18 | 
2 | SB2/US14 | User | if parking is not available | it will display that parking is not available. | 5 | Mahesh Meena | 23-Oct-18 | 
3 | SB3/US1 | User | prediction will be maintained for parking | till what time parking will be full. | 3 | Mahesh Meena | 23-Oct-18 | 
3 | SB3/US2 | User | separate spaces for two wheelers | two wheelers have different parking. | 4 | Mahesh Meena | 30-Oct-18 | 
3 | SB3/US3 | User | separate spaces for three wheelers | three wheelers have different parking. | 4 | Mahesh Meena | 30-Oct-18 | 
3 | SB3/US4 | User | separate spaces for four wheelers | four wheelers have different parking. | 4 | Mahesh Meena | 30-Oct-18 | 
3 | SB3/US5 | User | all the public parking lots will be covered | parking problems will be reduced. | 4 | Mahesh Meena | 30-Oct-18 | 
3 | SB3/US6 | User | if area has Parking Lot for two wheelers | only two wheelers vehicles will be parked | 5 | Mahesh Meena | 07-Oct-18 | 
3 | SB3/US7 | User | if area has Parking Lot for three wheelers | only three wheelers vehicles will be parked | 4 | Mahesh Meena | 07-Oct-18 | 
3 | SB3/US8 | User | if area has Parking Lot for four wheelers | only four wheelers vehicles will be parked | 4 | Mahesh Meena | 07-Oct-18 | 
3 | SB3/US9 | User | prediction will also tell that | till what time parking will be full or empty. | 1 | Mahesh Meena | 07-Oct-18 | 
3 | SB3/US10 | User | parking will be available only for selected areas | the areas will cover all the nearby parking lots. | 1 | Mahesh Meena | 07-Oct-18 | 
3 | SB3/US11 | User | two wheelers parking will be mentioned seperately | two wheelers can park seperately. | 1 | Mahesh Meena | 14-Oct-18 | 
3 | SB3/US12 | User | three wheelers parking will be mentioned separately | three wheelers can park seperately. | 3 | Mahesh Meena | 14-Oct-18 | 
3 | SB3/US13 | User | no parking charges will be there | as it is a free parking slot. | 2 | Mahesh Meena | 14-Oct-18 | 
4 | SB4/US1 | User | provide some driving tips | user can follow it for his/her own good. | 2 | Mahesh Meena | 14-Oct-18 | 
4 | SB4/US2 | Admin | put insert queries | I can insert new queries in the database. | 4 | Mahesh Meena | 14-Oct-18 | 
4 | SB4/US3 | Admin | put update queries | I can update the existing records. | 1 | Mahesh Meena | 21-Oct-18 | 
4 | SB4/US4 | Admin | put select queries | I can view the records. | 6 | Mahesh Meena | 21-Oct-18 | 
4 | SB4/US5 | Admin | put delete queries | I can remove the unwanted records. | 2 | Mahesh Meena | 21-Oct-18 | 
4 | SB4/US6 | Admin | take a backup | I can save old records for future use. | 2 | Mahesh Meena | 21-Oct-18 | 
4 | SB4/US7 | Admin | delete a backup | I can delete the unwanted backup. | 3 | Mahesh Meena | 21-Oct-18 | 
4 | SB4/US8 | Admin | can add new parking lot | if any other parking lot is built | 2 | Mahesh Meena | 00-Jan-00 | 
4 | SB4/US9 | Admin | can delete a parking lot | if parking lot is demolished | 1 | Mahesh Meena | 00-Jan-00 | 
4 | SB4/US10 | Admin | can add new area | for new parking lot | 1 | Mahesh Meena | 00-Jan-00 | 
4 | SB4/US11 | Admin | can delete area | if no parking lot is there in that area | 1 | Mahesh Meena | 00-Jan-00 | 
4 | SB4/US12 | User | give feedback or suggestions | the service can be improved. | 2 | Mahesh Meena | 00-Jan-00 | 

## Slide 7
Sprint Backlog -1
SPRINT BACKLOG 1 |  |  |  |  |  | 
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - Smart Parking System |  |  |  |  |  | 
SB1/US1 | open web portal | SB1/D1/T1 | Designing of GUI | Kartik Tiwari | In progress | 22-Sep-18
 |  | SB1/D1/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 22-Sep-18
 |  | SB1/D1/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 22-Sep-18
 |  | SB1/D1/T4 | Connection with Database to insert the data. | Kartik Tiwari | In progress | 22-Sep-18
 |  | SB1/D1/T5 | Testing of the module on localhost and then on server. | Kartik Tiwari | In progress | 22-Sep-18
SB1/US2 | Registers Himself/Herself | SB1/D2/T1 | Designing of GUI | Kartik Tiwari | In progress | 22-Sep-18
 |  | SB1/D2/T2 | Apply CSS | Kartik Tiwari | In progress | 29-Sep-18
 |  | SB1/D2/T3 | Connection with Database to insert the data. | Kartik Tiwari | In progress | 29-Sep-18
SB1/US3 | sign's in | SB1/D3/T1 | Designing of GUI | Kartik Tiwari | In progress | 29-Sep-18
 |  | SB1/D3/T2 | Apply CSS | Kartik Tiwari | Not Started | 29-Sep-18
 |  | SB1/D3/T3 | Connection with Database to insert the data. | Kartik Tiwari | Not Started | 02-Oct-18
SB1/US4 | will register only single parking lot | SB1/D4/T1 | Designing of GUI | Kartik Tiwari | Not Started | 02-Oct-18
 |  | SB1/D4/T2 | Validating user input at client level. | Kartik Tiwari | Not Started | 02-Oct-18
 |  | SB1/D4/T3 | Validating user input at server level. | Kartik Tiwari | Not Started | 02-Oct-18
 |  | SB1/D4/T4 | control the activities of vehicles. | Kartik Tiwari | Not Started | 02-Oct-18
SB1/US5 | will keep record of vehicles | SB1/D5/T1 | Apply CSS | Kartik Tiwari | Not Started | 09-Oct-18
 |  | SB1/D5/T2 | Creating connection file in jsp for database connectivity. | Kartik Tiwari | Not Started | 09-Oct-18
 |  | SB1/D5/T3 | insert parking slots chosen into the database. | Kartik Tiwari | Not Started | 09-Oct-18
SB1/US6 | mention the number of spaces available | SB1/D6/T1 | Apply CSS | Kartik Tiwari | Not Started | 09-Oct-18
 |  | SB1/D6/T2 | Creating connection file in jsp for database connectivity. | Kartik Tiwari | Not Started | 16-Oct-18
 |  | SB1/D6/T3 | insert all the parking slots chosen into the database. | Kartik Tiwari | Not Started | 16-Oct-18
SB1/US7 | mention the time period of availability of spaces | SB1/D7/T1 | Designing of GUI | Kartik Tiwari | Not Started | 16-Oct-18
 |  | SB1/D7/T2 | Validating user input at client level. | Kartik Tiwari | Not Started | 16-Oct-18
 |  | SB1/D7/T3 | Validating user input at server level. | Kartik Tiwari | Not Started | 16-Oct-18
 |  | SB1/D7/T4 | Analysis of parking slots to predict the available parkings. | Kartik Tiwari | Not Started | 23-Oct-18
SB1/US8 | control incoming vehicles | SB1/D8/T1 | Designing of GUI | Mahesh Meena | Not Started | 23-Oct-18
 |  | SB1/D8/T2 | Apply JSP | Mahesh Meena | Not Started | 23-Oct-18
 |  | SB1/D8/T3 | Connection with Database to change the number of spaces. | Mahesh Meena | Not Started | 23-Oct-18
 |  | SB1/D8/T4 | Fetching of value of number of spaces available. | Mahesh Meena | Not Started | 30-Oct-18
SB1/US9 | control outgoing vehicles | SB1/D9/T1 | Designing of GUI | Mahesh Meena | Not Started | 30-Oct-18
 |  | SB1/D9/T2 | Validating user input at client level. | Mahesh Meena | Not Started | 30-Oct-18
 |  | SB1/D9/T3 | Validating user input at server level. | Mahesh Meena | Not Started | 30-Oct-18
 |  | SB1/D9/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Not Started | 07-Oct-18
SB1/US10 | register only free parking lots | SB1/D10/T1 | Designing of GUI | Mahesh Meena | Not Started | 07-Oct-18
 |  | SB1/D10/T2 | Validating user input at client level. | Mahesh Meena | Not Started | 07-Oct-18
 |  | SB1/D10/T3 | Validating user input at server level. | Mahesh Meena | Not Started | 07-Oct-18
 |  | SB1/D10/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Not Started | 07-Oct-18
SB1/US11 | cover all the parking lots | SB1/D11/T1 | Designing of GUI | Mahesh Meena | Not Started | 14-Oct-18
 |  | SB1/D11/T2 | Validating user input at client level. | Mahesh Meena | Not Started | 14-Oct-18
 |  | SB1/D11/T3 | Validating user input at server level. | Mahesh Meena | Not Started | 14-Oct-18
 |  | SB1/D11/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Not Started | 14-Oct-18
SB1/US12 | predict the available parkings | SB1/D12/T1 | Designing of GUI | Mahesh Meena | Not Started | 14-Oct-18
 |  | SB1/D12/T2 | Validating user input at client level. | Mahesh Meena | Not Started | 21-Oct-18
 |  | SB1/D12/T3 | Validating user input at server level. | Mahesh Meena | Not Started | 21-Oct-18
 |  | SB1/D12/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Not Started | 21-Oct-18
SB1/US13 | change the number od spaces automatically | SB1/D13/T1 | Designing of GUI | Mahesh Meena | Not Started | 21-Oct-18
 |  | SB1/D13/T2 | Validating user input at client level. | Mahesh Meena | Not Started | 21-Oct-18
 |  | SB1/D13/T3 | Validating user input at server level. | Mahesh Meena | Not Started | 21-Oct-18
 |  | SB1/D13/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Not Started | 28-Oct-18

## Slide 8: Sprint Backlog -2
SPRINT BACKLOG 2 |  |  |  |  |  | 
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - Smart Parking System |  |  |  |  |  | 
SB2/US1 | display message if parking is available | SB2/D1/T1 | Designing of GUI | Kartik Tiwari | Completed | 29-Sep-18
 |  | SB2/D1/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 29-Sep-18
 |  | SB2/D1/T3 | Fetching of parking slots. | Kartik Tiwari | Completed | 29-Sep-18
 |  | SB2/D1/T4 | Displaying the message. | Kartik Tiwari | Completed | 29-Sep-18
SB2/US2 | display all the nearby parking slots | SB2/D2/T1 | Designing of GUI | Kartik Tiwari | Completed | 02-Oct-18
 |  | SB2/D2/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 02-Oct-18
 |  | SB2/D2/T3 | Fetching of all the nearby parking slots. | Kartik Tiwari | Completed | 02-Oct-18
 |  | SB2/D2/T4 | Displaying the message. | Kartik Tiwari | Completed | 02-Oct-18
SB2/US3 | paid parking has different criteria | SB2/D3/T1 | Designing of GUI | Kartik Tiwari | Completed | 02-Oct-18
 |  | SB2/D3/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 09-Oct-18
 |  | SB2/D3/T3 | if paid parking is found then give the different criteria | Kartik Tiwari | Completed | 09-Oct-18
SB2/US4 | open web portal | SB2/D4/T1 | Designing of GUI | Kartik Tiwari | Completed | 09-Oct-18
 |  | SB2/D4/T2 | Validating user input at client level | Kartik Tiwari | Completed | 09-Oct-18
 |  | SB2/D4/T3 | Validating user input at server level | Kartik Tiwari | Completed | 16-Oct-18
 |  | SB2/D4/T4 | Connection with Database to insert the record. | Kartik Tiwari | Completed | 16-Oct-18
 |  | SB2/D4/T5 | Testing of the module on localhost and then on server. | Kartik Tiwari | Completed | 16-Oct-18
SB2/US5 | display the parking lots | SB2/D5/T1 | Designing of GUI | Kartik Tiwari | Completed | 16-Oct-18
 |  | SB2/D5/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 16-Oct-18
 |  | SB2/D5/T3 | Fetching of all the parking slots. | Kartik Tiwari | Completed | 23-Oct-18
 |  | SB2/D5/T4 | Display the parking slots via CSS. | Mahesh Meena | Completed | 23-Oct-18
SB2/US6 | if parking is available | SB2/D6/T1 | Designing of GUI | Mahesh Meena | Completed | 23-Oct-18
 |  | SB2/D6/T2 | Validating user input at client level | Mahesh Meena | Completed | 23-Oct-18
 |  | SB2/D6/T3 | Validating user input at server level | Mahesh Meena | Completed | 30-Oct-18
 |  | SB2/D6/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 30-Oct-18
 |  | SB2/D6/T5 | Check the number of spaces available. | Mahesh Meena | Completed | 30-Oct-18
SB2/US7 | is free to see parking availability | SB2/D7/T1 | Designing of GUI | Mahesh Meena | Completed | 30-Oct-18
 |  | SB2/D7/T2 | Validating user input at client level | Mahesh Meena | Completed | 07-Oct-18
 |  | SB2/D7/T3 | Validating user input at server level | Mahesh Meena | Completed | 07-Oct-18
 |  | SB2/D7/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 07-Oct-18
 |  | SB2/D7/T5 | Check the most usual time period of empty parking. | Mahesh Meena | Completed | 07-Oct-18
SB2/US8 | is free to see parking availability anytime | SB2/D8/T1 | Designing of GUI | Mahesh Meena | Completed | 07-Oct-18
 |  | SB2/D8/T2 | Validating user input at client level | Mahesh Meena | Completed | 14-Oct-18
 |  | SB2/D8/T3 | Validating user input at server level | Mahesh Meena | Completed | 14-Oct-18
 |  | SB2/D8/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 14-Oct-18
 |  | SB2/D8/T5 | Display the availability of parkings. | Mahesh Meena | Completed | 14-Oct-18
SB2/US9 | can see Parking with normal Internet Connection | SB2/D9/T1 | Designing of GUI | Mahesh Meena | Completed | 14-Oct-18
 |  | SB2/D9/T2 | Validating user input at client level | Mahesh Meena | Completed | 21-Oct-18
 |  | SB2/D9/T3 | Validating user input at server level | Mahesh Meena | Completed | 21-Oct-18
 |  | SB2/D9/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 21-Oct-18
SB2/US10 | prediction of two wheelers | SB2/D10/T1 | Designing of GUI | Mahesh Meena | Completed | 21-Oct-18
 |  | SB2/D10/T2 | Validating user input at client level | Mahesh Meena | Completed | 21-Oct-18
 |  | SB2/D10/T3 | Validating user input at server level | Mahesh Meena | Completed | 21-Oct-18
 |  | SB2/D10/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 22-Oct-18
SB2/US11 | prediction of three wheelers | SB2/D11/T1 | Designing of GUI | Mahesh Meena | Completed | 23-Oct-18
 |  | SB2/D11/T2 | Validating user input at client level | Mahesh Meena | Completed | 24-Oct-18
 |  | SB2/D11/T3 | Validating user input at server level | Mahesh Meena | Completed | 25-Oct-18
 |  | SB2/D11/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 26-Oct-18
SB2/US12 | prediction of four wheelers | SB2/D12/T1 | Designing of GUI | Mahesh Meena | Completed | 27-Oct-18
 |  | SB2/D12/T2 | Validating user input at client level | Mahesh Meena | Completed | 28-Oct-18
 |  | SB2/D12/T3 | Validating user input at server level | Mahesh Meena | Completed | 28-Oct-18
 |  | SB2/D12/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 28-Oct-18
SB2/US13 | it will predict that | SB2/D13/T1 | Designing of GUI | Mahesh Meena | Completed | 28-Oct-18
 |  | SB2/D13/T2 | Validating user input at client level | Mahesh Meena | In progress | 28-Oct-18
 |  | SB2/D13/T3 | Validating user input at server level | Mahesh Meena | In progress | 28-Oct-18
 |  | SB2/D13/T4 | Connection with Database to search the record. | Mahesh Meena | In progress | 28-Oct-18
SB2/US14 | if parking is not available | SB2/D14/T1 | Designing of GUI | Mahesh Meena | In progress | 28-Oct-18
 |  | SB2/D14/T2 | Validating user input at client level | Mahesh Meena | In progress | 28-Oct-18
 |  | SB2/D14/T3 | Validating user input at server level | Mahesh Meena | In progress | 28-Oct-18
 |  | SB2/D14/T4 | Connection with Database to search the record. | Mahesh Meena | In progress | 28-Oct-18

## Slide 9: Sprint Backlog -3
SPRINT BACKLOG 3 |  |  |  |  |  | 
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - Smart Parking System |  |  |  |  |  | 
SB3/US1 | till what time parking will be full | SB3/D1/T1 | Designing of GUI | Aniket Mathur | Completed | 01 Jan. 2019
 |  | SB3/D1/T2 | Validating user input at client level. | Aniket Mathur | Completed | 2 Jan. 2019
 |  | SB3/D1/T3 | Validating user input at server level. | Aniket Mathur | Completed | 3 Jan. 2019
 |  | SB3/D1/T4 | Mention available time for full parking | Aniket Mathur | Completed | 4 Jan. 2019
SB3/US2 | separate spaces for multiple vehicles | SB3/D2/T1 | Designing of GUI | Aniket Mathur | Completed | 5 Jan. 2019
 |  | SB3/D2/T2 | Validating user input at client level. | Aniket Mathur | Completed | 6 Jan. 2019
 |  | SB3/D2/T3 | Validating user input at server level. | Aniket Mathur | Completed | 7 Jan. 2019
 |  | SB3/D2/T4 | Connection with Database to insert the separate spaces. | Aniket Mathur | Completed | 8 Jan. 2019
 |  | SB3/D2/T5 | Different vehicles choose different spaces. | Aniket Mathur | Completed | 9 Jan. 2019
SB3/US3 | all public parking slots will be covered | SB3/D3/T1 | Designing of GUI | Aniket Mathur | Completed | 10 Jan. 2019
 |  | SB3/D3/T2 | Validating user input at client level. | Aniket Mathur | Completed | 11 Jan. 2019
 |  | SB3/D3/T3 | Validating user input at server level. | Aniket Mathur | Completed | 12 Jan. 2019
 |  | SB3/D3/T4 | Fetching of all the public parking slots. | Kartik Tiwari | Completed | 13 Jan. 2019
SB3/US4 | till what time parking will be empty | SB3/D4/T1 | Designing of GUI | Kartik Tiwari | Completed | 14 Jan. 2019
 |  | SB3/D4/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 1 Feb. 2019
 |  | SB3/D4/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 2 Feb. 2019
 |  | SB3/D4/T4 | Mention available time for empty parking | Kartik Tiwari | Completed | 3 Feb. 2019
SB3/US5 | parking will be available only for selected areas | SB3/D5/T1 | Designing of GUI | Kartik Tiwari | Completed | 4 Feb. 2019
 |  | SB3/D5/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 5 Feb. 2019
 |  | SB3/D5/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 6 Feb. 2019
 |  | SB3/D5/T4 | Connection with Database to insert the selected areas. | Kartik Tiwari | Completed | 7 Feb. 2019
 |  | SB3/D5/T5 | Matching of selected areas to the parkings. | Kartik Tiwari | Completed | 8 Feb. 2019
SB3/US6 | two wheelers will park seperately | SB3/D6/T1 | Designing of GUI | Kartik Tiwari | Completed | 9 Feb. 2019
 |  | SB3/D6/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 10 Feb. 2019
 |  | SB3/D6/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 11 Feb. 2019
 |  | SB3/D6/T4 | Connection with Database to insert parking for two wheelers. | Mahesh Meena | Completed | 12 Feb. 2019
 |  | SB3/D6/T5 | arrange vehicles according to their type. | Mahesh Meena | Completed | 13 Feb. 2019
SB3/US7 | three wheelers will park separately | SB3/D7/T1 | Designing of GUI | Mahesh Meena | Completed | 14 Feb. 2019
 |  | SB3/D7/T2 | Validating user input at client level. | Mahesh Meena | Completed | 15 Feb. 2019
 |  | SB3/D7/T3 | Validating user input at server level. | Mahesh Meena | Completed | 16 Feb. 2019
 |  | SB3/D7/T4 | Connection with Database to insert parking for three wheelers. | Mahesh Meena | Completed | 17 Feb. 2019
 |  | SB3/D7/T5 | arrange vehicles according to their type. | Mahesh Meena | Completed | 18 Feb. 2019
SB3/US8 | No parking charges will be there | SB3/D8/T1 | Designing of GUI | Mahesh Meena | Completed | 19 Feb. 2019
 |  | SB3/D8/T2 | Connection with Database to insert the data. | Mahesh Meena | Completed | 20 Feb. 2019
 |  | SB3/D8/T3 | no charges will be applied for parking. | Mahesh Meena | Completed | 21 Feb. 2019

## Slide 10: Sprint Backlog -4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - Smart Parking System |  |  |  |  |  | 
SB4/US1 | provide some driving tips | SB4/D1/T1 | Creating a web page including driving tips. | Aniket Mathur | In progress | 01-03-2019
 |  | SB4/D1/T2 | Apply CSS. | Aniket Mathur | In progress | 02-03-2019
 |  | SB4/D1/T3 | Apply Designing. | Aniket Mathur | In progress | 03-03-2019
SB4/US2 | put insert queries | SB4/D2/T1 | Designing of GUI | Aniket Mathur | In progress | 04-03-2019
 |  | SB4/D2/T2 | Validating user input at client level. | Aniket Mathur | In progress | 05-03-2019
 |  | SB4/D2/T3 | Validating user input at server level. | Aniket Mathur | In progress | 06-03-2019
 |  | SB4/D2/T4 | Connection with Database to insert the parking records. | Aniket Mathur | In progress | 07-03-2019
SB4/US3 | put update queries | SB4/D3/T1 | Designing of GUI | Aniket Mathur | In progress | 08-03-2019
 |  | SB4/D3/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 09-03-2019
 |  | SB4/D3/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 10-03-2019
 |  | SB4/D3/T4 | Connection with Database to update the parking records. | Kartik Tiwari | In progress | 11-03-2019
SB4/US4 | put select queries | SB4/D4/T1 | Designing of GUI | Kartik Tiwari | In progress | 12-03-2019
 |  | SB4/D4/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 13-03-2019
 |  | SB4/D4/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 14-03-2019
 |  | SB4/D4/T4 | Connection with Database to search the parking records. | Kartik Tiwari | In progress | 15-03-2019
SB4/US5 | put delete queries | SB4/D5/T1 | Designing of GUI | Kartik Tiwari | In progress | 16-03-2019
 |  | SB4/D5/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 17-03-2019
 |  | SB4/D5/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 18-03-2019
 |  | SB4/D5/T4 | Connection with Database to delere the parking records. | Kartik Tiwari | In progress | 19-03-2019
SB4/US6 | Take a backup | SB4/D6/T1 | Designing of GUI | Kartik Tiwari | In progress | 20-03-2019
 |  | SB4/D6/T2 | Validating user input at client level. | Mahesh Meena | In progress | 21-03-2019
 |  | SB4/D6/T3 | Validating user input at server level. | Mahesh Meena | In progress | 22-03-2019
 |  | SB4/D6/T4 | Connection with Database to take a backup of parkings. | Mahesh Meena | In progress | 23-03-2019
SB4/US7 | Delete a backup | SB4/D7/T1 | Designing of GUI | Mahesh Meena | In progress | 24-03-2019
 |  | SB4/D7/T2 | Validating user input at client level. | Mahesh Meena | In progress | 25-03-2019
 |  | SB4/D7/T3 | Validating user input at server level. | Mahesh Meena | In progress | 26-03-2019
 |  | SB4/D7/T4 | Connection with Database to delete an existing backup. | Mahesh Meena | In progress | 27-03-2019
SB4/US8 | Give feedback or suggestions | SB4/D8/T1 | Designing of GUI | Mahesh Meena | In progress | 28-03-2019
 |  | SB4/D8/T2 | Validating user input at client level. | Mahesh Meena | In progress | 29-03-2019
 |  | SB4/D8/T3 | Validating user input at server level. | Mahesh Meena | In progress | 30-03-2019
 |  | SB4/D8/T4 | Connection with Database to insert the user's feedback. | Mahesh Meena | In progress | 31-03-2019
 |  | SB4/D8/T5 | Testing the module on localhost & then on server. | Mahesh Meena | In progress | 01-04-2019

## Slide 11: Results
Fixed parking were seen in the Parking Lots after the Portal was made.
People will plan accordingly that Parking is available or not.
More and More Vehicles can be parked in Paid Parking Lots.

## Slide 12: Conclusion and Future Scope
The problem of parking was solved as various users were taking the help of portal to see whether the parking is available or not.
In Future, Everyone will be able to see the availability in the Mobile App only.
More areas will be added to the App as a whole city will be covered in the App and all parking lots will be there on the App.

## Slide 13
Thanks