## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | open web portal | admin can register free parking lots. | 1 | Kartik Tiwari | 2018-09-22
1 | SB1/US2 | Admin | Registers Himself/Herself | parking lot can be verified | 2 | Kartik Tiwari | 2018-09-22
1 | SB1/US3 | Admin | sign's in | admin puts his/her parking lot | 3 | Kartik Tiwari | 2018-09-22
1 | SB1/US4 | Admin | will register only single parking lot | each admin is associated with one parking lot | 1 | Kartik Tiwari | 2018-09-22
1 | SB1/US5 | Admin | will keep record of vehicles | no vehicle is stolen | 2 | Kartik Tiwari | 2018-09-22
1 | SB1/US6 | Admin | mention the number of spaces available | user can park vehicles. | 2 | Kartik Tiwari | 2018-09-22
1 | SB1/US7 | Admin | mention the time period of availability of spaces | parking problems will be reduced. | 1 | Kartik Tiwari | 2018-09-29
1 | SB1/US8 | Admin | control incoming vehicles | number of spaces will decrease. | 2 | Kartik Tiwari | 2018-09-29
1 | SB1/US9 | Admin | control outgoing vehicles | number of spaces will increase | 2 | Kartik Tiwari | 2018-09-29
1 | SB1/US10 | Admin | register only free parking lots | user can park their vehicles. | 1 | Kartik Tiwari | 2018-09-29
1 | SB1/US11 | Admin | cover all the parking lots | parking problems will reduce in that area. | 1 | Kartik Tiwari | 2018-10-02
1 | SB1/US12 | Admin | predict the available parkings | I can interact with the tools of application. | 1 | Kartik Tiwari | 2018-10-02
1 | SB1/US13 | Admin | change the number of spaces automatically | user can see available spaces. | 1 | Kartik Tiwari | 2018-10-02
2 | SB2/US1 | Admin | display message if the parking is available | user can look for another parking. | 4 | Kartik Tiwari | 2018-10-02
2 | SB2/US2 | Admin | display all the nearby parking lots | user can choose his/her suitable parking. | 4 | Kartik Tiwari | 2018-10-02
2 | SB2/US3 | Admin | paid parking has different criteria | admin will not include paid parking. | 5 | Kartik Tiwari | 2018-10-09
2 | SB2/US4 | User | open web portal | enter particular area | 1 | Kartik Tiwari | 2018-10-09
2 | SB2/US5 | User | display the parking lots | user can click on a particular parking slot. | 1 | Kartik Tiwari | 2018-10-09
2 | SB2/US6 | User | if parking is available | it will show how many spaces are available. | 1 | Kartik Tiwari | 2018-10-09
2 | SB2/US7 | User | is free to see parking availability | no charges will be there | 1 | Kartik Tiwari | 2018-10-16
2 | SB2/US8 | User | is free to see parking availability anytime | no time boundations will be there | 1 | Kartik Tiwari | 2018-10-16
2 | SB2/US9 | User | can see Parking with normal Internet Connection | No Fast Internet will be needed | 1 | Kartik Tiwari | 2018-10-16
2 | SB2/US10 | User | prediction of two wheelers | will be shown separate for two wheelers | 2 | Kartik Tiwari | 2018-10-16
2 | SB2/US11 | User | prediction of three wheelers | will be shown separate for three wheelers | 5 | Kartik Tiwari | 2018-10-16
2 | SB2/US12 | User | prediction of four wheelers | will be shown separate for four wheelers | 4 | Kartik Tiwari | 2018-10-23
2 | SB2/US13 | User | it will predict that | till when the parking will be available. | 4 | Kartik Tiwari | 2018-10-23
2 | SB2/US14 | User | if parking is not available | it will display that parking is not available. | 5 | Mahesh Meena | 2018-10-23
3 | SB3/US1 | User | prediction will be maintained for parking | till what time parking will be full. | 3 | Mahesh Meena | 2018-10-23
3 | SB3/US2 | User | separate spaces for two wheelers | two wheelers have different parking. | 4 | Mahesh Meena | 2018-10-30
3 | SB3/US3 | User | separate spaces for three wheelers | three wheelers have different parking. | 4 | Mahesh Meena | 2018-10-30
3 | SB3/US4 | User | separate spaces for four wheelers | four wheelers have different parking. | 4 | Mahesh Meena | 2018-10-30
3 | SB3/US5 | User | all the public parking lots will be covered | parking problems will be reduced. | 4 | Mahesh Meena | 2018-10-30
3 | SB3/US6 | User | if area has Parking Lot for two wheelers | only two wheelers vehicles will be parked | 5 | Mahesh Meena | 2018-10-07
3 | SB3/US7 | User | if area has Parking Lot for three wheelers | only three wheelers vehicles will be parked | 4 | Mahesh Meena | 2019-01-01
3 | SB3/US8 | User | if area has Parking Lot for four wheelers | only four wheelers vehicles will be parked | 4 | Mahesh Meena | 2019-01-02
3 | SB3/US9 | User | prediction will also tell that | till what time parking will be full or empty. | 1 | Mahesh Meena | 2019-01-03
3 | SB3/US10 | User | parking will be available only for selected areas | the areas will cover all the nearby parking lots. | 1 | Mahesh Meena | 2019-01-04
3 | SB3/US11 | User | two wheelers parking will be mentioned seperately | two wheelers can park seperately. | 1 | Mahesh Meena | 2019-01-05
3 | SB3/US12 | User | three wheelers parking will be mentioned separately | three wheelers can park seperately. | 3 | Mahesh Meena | 2019-01-06
3 | SB3/US13 | User | no parking charges will be there | as it is a free parking slot. | 2 | Mahesh Meena | 2019-01-07
4 | SB4/US1 | User | provide some driving tips | user can follow it for his/her own good. | 2 | Mahesh Meena | 2019-01-08
4 | SB4/US2 | Admin | put insert queries | I can insert new queries in the database. | 4 | Mahesh Meena | 2019-01-09
4 | SB4/US3 | Admin | put update queries | I can update the existing records. | 1 | Mahesh Meena | 2019-01-10
4 | SB4/US4 | Admin | put select queries | I can view the records. | 6 | Mahesh Meena | 2019-02-01
4 | SB4/US5 | Admin | put delete queries | I can remove the unwanted records. | 2 | Mahesh Meena | 2019-02-02
4 | SB4/US6 | Admin | take a backup | I can save old records for future use. | 2 | Mahesh Meena | 2019-02-03
4 | SB4/US7 | Admin | delete a backup | I can delete the unwanted backup. | 3 | Mahesh Meena | 2019-02-04
4 | SB4/US8 | Admin | can add new parking lot | if any other parking lot is built | 2 | Mahesh Meena | 2019-02-05
4 | SB4/US9 | Admin | can delete a parking lot | if parking lot is demolished | 1 | Mahesh Meena | 2019-02-06
4 | SB4/US10 | Admin | can add new area | for new parking lot | 1 | Mahesh Meena | 2019-02-07
4 | SB4/US11 | Admin | can delete area | if no parking lot is there in that area | 1 | Mahesh Meena | 2019-02-08
4 | SB4/US12 | User | give feedback or suggestions | the service can be improved. | 2 | Mahesh Meena | 2019-02-09
Formulas:
ESTIMATE DATE = [1]ProductBacklog!H5

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - Smart Parking System
SB1/US1 | open web portal | SB1/D1/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-09-22
|  | SB1/D1/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 2018-09-22
|  | SB1/D1/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 2018-09-22
|  | SB1/D1/T4 | Connection with Database to insert the data. | Kartik Tiwari | Completed | 2018-09-22
|  | SB1/D1/T5 | Testing of the module on localhost and then on server. | Kartik Tiwari | Completed | 2018-09-22
SB1/US2 | Registers Himself/Herself | SB1/D2/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-09-22
|  | SB1/D2/T2 | Apply CSS | Kartik Tiwari | Completed | 2018-09-29
|  | SB1/D2/T3 | Connection with Database to insert the data. | Kartik Tiwari | Completed | 2018-09-29
SB1/US3 | sign's in | SB1/D3/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-09-29
|  | SB1/D3/T2 | Apply CSS | Kartik Tiwari | Completed | 2018-09-29
|  | SB1/D3/T3 | Connection with Database to insert the data. | Kartik Tiwari | Completed | 2018-10-02
SB1/US4 | will register only single parking lot | SB1/D4/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-02
| will register only single parking lot | SB1/D4/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 2018-10-02
| will register only single parking lot | SB1/D4/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 2018-10-02
| will register only single parking lot | SB1/D4/T4 | control the activities of vehicles. | Kartik Tiwari | Completed | 2018-10-02
SB1/US5 | will keep record of vehicles | SB1/D5/T1 | Apply CSS | Kartik Tiwari | Completed | 2018-10-09
| mention the number of spaces available | SB1/D5/T2 | Creating connection file in jsp for database connectivity. | Kartik Tiwari | Completed | 2018-10-09
| mention the time period of availability of spaces | SB1/D5/T3 | insert parking slots chosen into the database. | Kartik Tiwari | Completed | 2018-10-09
SB1/US6 | mention the number of spaces available | SB1/D6/T1 | Apply CSS | Kartik Tiwari | Completed | 2018-10-09
| mention the number of spaces available | SB1/D6/T2 | Creating connection file in jsp for database connectivity. | Kartik Tiwari | Completed | 2018-10-16
| mention the number of spaces available | SB1/D6/T3 | insert all the parking slots chosen into the database. | Kartik Tiwari | Completed | 2018-10-16
SB1/US7 | mention the time period of availability of spaces | SB1/D7/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-16
| mention the time period of availability of spaces | SB1/D7/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 2018-10-16
| mention the time period of availability of spaces | SB1/D7/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 2018-10-16
| mention the time period of availability of spaces | SB1/D7/T4 | Analysis of parking slots to predict the available parkings. | Kartik Tiwari | Completed | 2018-10-23
SB1/US8 | control incoming vehicles | SB1/D8/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-23
| control outgoing vehicles | SB1/D8/T2 | Apply JSP | Mahesh Meena | Completed | 2018-10-23
| control incoming vehicles | SB1/D8/T3 | Connection with Database to change the number of spaces. | Mahesh Meena | Completed | 2018-10-23
| control outgoing vehicles | SB1/D8/T4 | Fetching of value of number of spaces available. | Mahesh Meena | Completed | 2018-10-30
SB1/US9 | control outgoing vehicles | SB1/D9/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-30
| control outgoing vehicles | SB1/D9/T2 | Validating user input at client level. | Mahesh Meena | Completed | 2018-10-30
| control outgoing vehicles | SB1/D9/T3 | Validating user input at server level. | Mahesh Meena | Completed | 2018-10-30
| control outgoing vehicles | SB1/D9/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Completed | 2018-10-07
SB1/US10 | register only free parking lots | SB1/D10/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-07
| register only free parking lots | SB1/D10/T2 | Validating user input at client level. | Mahesh Meena | Completed | 2018-10-07
| register only free parking lots | SB1/D10/T3 | Validating user input at server level. | Mahesh Meena | Completed | 2018-10-07
| register only free parking lots | SB1/D10/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Completed | 2018-10-07
SB1/US11 | cover all the parking lots | SB1/D11/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-14
| cover all the parking lots | SB1/D11/T2 | Validating user input at client level. | Mahesh Meena | Completed | 2018-10-14
| cover all the parking lots | SB1/D11/T3 | Validating user input at server level. | Mahesh Meena | Completed | 2018-10-14
| cover all the parking lots | SB1/D11/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Completed | 2018-10-14
SB1/US12 | predict the available parkings | SB1/D12/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-14
| predict the available parkings | SB1/D12/T2 | Validating user input at client level. | Mahesh Meena | Completed | 2018-10-21
| predict the available parkings | SB1/D12/T3 | Validating user input at server level. | Mahesh Meena | Completed | 2018-10-21
| predict the available parkings | SB1/D12/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Completed | 2018-10-21
SB1/US13 | change the number od spaces automatically | SB1/D13/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-21
| change the number od spaces automatically | SB1/D13/T2 | Validating user input at client level. | Mahesh Meena | Completed | 2018-10-21
| change the number od spaces automatically | SB1/D13/T3 | Validating user input at server level. | Mahesh Meena | Completed | 2018-10-21
| change the number od spaces automatically | SB1/D13/T4 | Analysis of parking slots to predict the available parkings. | Mahesh Meena | Completed | 2018-10-28

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 29 | 29 | Tasks
2018-09-09 | 19 | 29
2018-09-11 | 15 | 29
2018-09-14 | 8 | 29
2018-09-16 | 4 | 29
2018-09-18 | 0 | 29
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - Smart Parking System
SB2/US1 | display message if parking is available | SB2/D1/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-09-29
|  | SB2/D1/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 2018-09-29
|  | SB2/D1/T3 | Fetching of parking slots. | Kartik Tiwari | Completed | 2018-09-29
|  | SB2/D1/T4 | Displaying the message. | Kartik Tiwari | Completed | 2018-09-29
SB2/US2 | display all the nearby parking slots | SB2/D2/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-02
|  | SB2/D2/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 2018-10-02
|  | SB2/D2/T3 | Fetching of all the nearby parking slots. | Kartik Tiwari | Completed | 2018-10-02
|  | SB2/D2/T4 | Displaying the message. | Kartik Tiwari | Completed | 2018-10-02
SB2/US3 | paid parking has different criteria | SB2/D3/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-02
|  | SB2/D3/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 2018-10-09
|  | SB2/D3/T3 | if paid parking is found then give the different criteria | Kartik Tiwari | Completed | 2018-10-09
SB2/US4 | open web portal | SB2/D4/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-09
|  | SB2/D4/T2 | Validating user input at client level | Kartik Tiwari | Completed | 2018-10-09
|  | SB2/D4/T3 | Validating user input at server level | Kartik Tiwari | Completed | 2018-10-16
|  | SB2/D4/T4 | Connection with Database to insert the record. | Kartik Tiwari | Completed | 2018-10-16
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | Kartik Tiwari | Completed | 2018-10-16
SB2/US5 | display the parking lots | SB2/D5/T1 | Designing of GUI | Kartik Tiwari | Completed | 2018-10-16
|  | SB2/D5/T2 | Connection with database to fetch the data | Kartik Tiwari | Completed | 2018-10-16
|  | SB2/D5/T3 | Fetching of all the parking slots. | Kartik Tiwari | Completed | 2018-10-23
|  | SB2/D5/T4 | Display the parking slots via CSS. | Mahesh Meena | Completed | 2018-10-23
SB2/US6 | if parking is available | SB2/D6/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-23
|  | SB2/D6/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-23
|  | SB2/D6/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-30
|  | SB2/D6/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-30
|  | SB2/D6/T5 | Check the number of spaces available. | Mahesh Meena | Completed | 2018-10-30
SB2/US7 | is free to see parking availability | SB2/D7/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-30
|  | SB2/D7/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-07
|  | SB2/D7/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-07
|  | SB2/D7/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-07
|  | SB2/D7/T5 | Check the most usual time period of empty parking. | Mahesh Meena | Completed | 2018-10-07
SB2/US8 | is free to see parking availability anytime | SB2/D8/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-07
|  | SB2/D8/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-14
|  | SB2/D8/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-14
|  | SB2/D8/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-14
|  | SB2/D8/T5 | Display the availability of parkings. | Mahesh Meena | Completed | 2018-10-14
SB2/US9 | can see Parking with normal Internet Connection | SB2/D9/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-14
|  | SB2/D9/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-21
|  | SB2/D9/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-21
|  | SB2/D9/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-21
SB2/US10 | prediction of two wheelers | SB2/D10/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-21
|  | SB2/D10/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-21
|  | SB2/D10/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-21
|  | SB2/D10/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-22
SB2/US11 | prediction of three wheelers | SB2/D11/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-23
|  | SB2/D11/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-24
|  | SB2/D11/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-25
|  | SB2/D11/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-26
SB2/US12 | prediction of four wheelers | SB2/D12/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-27
|  | SB2/D12/T2 | Validating user input at client level | Mahesh Meena | Completed | 2018-10-28
|  | SB2/D12/T3 | Validating user input at server level | Mahesh Meena | Completed | 2018-10-28
|  | SB2/D12/T4 | Connection with Database to search the record. | Mahesh Meena | Completed | 2018-10-28
SB2/US13 | it will predict that | SB2/D13/T1 | Designing of GUI | Mahesh Meena | Completed | 2018-10-28
|  | SB2/D13/T2 | Validating user input at client level | Mahesh Meena | In progress | 2018-10-28
|  | SB2/D13/T3 | Validating user input at server level | Mahesh Meena | In progress | 2018-10-28
|  | SB2/D13/T4 | Connection with Database to search the record. | Mahesh Meena | In progress | 2018-10-28
SB2/US14 | if parking is not available | SB2/D14/T1 | Designing of GUI | Mahesh Meena | In progress | 2018-10-28
|  | SB2/D14/T2 | Validating user input at client level | Mahesh Meena | In progress | 2018-10-28
|  | SB2/D14/T3 | Validating user input at server level | Mahesh Meena | In progress | 2018-10-28
|  | SB2/D14/T4 | Connection with Database to search the record. | Mahesh Meena | In progress | 2018-10-28

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 35 | 35 | Tasks
2017-09-28 | 28 | 35
2017-10-02 | 20 | 35
2017-10-05 | 13 | 35
2017-10-07 | 7 | 35
2017-10-09 | 0 | 35
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - Smart Parking System
SB3/US1 | till what time parking will be full | SB3/D1/T1 | Designing of GUI | Aniket Mathur | Completed | 01 Jan. 2019
|  | SB3/D1/T2 | Validating user input at client level. | Aniket Mathur | Completed | 2 Jan. 2019
|  | SB3/D1/T3 | Validating user input at server level. | Aniket Mathur | Completed | 3 Jan. 2019
|  | SB3/D1/T4 | Mention available time for full parking | Aniket Mathur | Completed | 4 Jan. 2019
SB3/US2 | separate spaces for multiple vehicles | SB3/D2/T1 | Designing of GUI | Aniket Mathur | Completed | 5 Jan. 2019
|  | SB3/D2/T2 | Validating user input at client level. | Aniket Mathur | Completed | 6 Jan. 2019
|  | SB3/D2/T3 | Validating user input at server level. | Aniket Mathur | Completed | 7 Jan. 2019
|  | SB3/D2/T4 | Connection with Database to insert the separate spaces. | Aniket Mathur | Completed | 8 Jan. 2019
|  | SB3/D2/T5 | Different vehicles choose different spaces. | Aniket Mathur | Completed | 9 Jan. 2019
SB3/US3 | all public parking slots will be covered | SB3/D3/T1 | Designing of GUI | Aniket Mathur | Completed | 10 Jan. 2019
|  | SB3/D3/T2 | Validating user input at client level. | Aniket Mathur | Completed | 11 Jan. 2019
|  | SB3/D3/T3 | Validating user input at server level. | Aniket Mathur | Completed | 12 Jan. 2019
|  | SB3/D3/T4 | Fetching of all the public parking slots. | Kartik Tiwari | Completed | 13 Jan. 2019
SB3/US4 | till what time parking will be empty | SB3/D4/T1 | Designing of GUI | Kartik Tiwari | Completed | 14 Jan. 2019
|  | SB3/D4/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 1 Feb. 2019
|  | SB3/D4/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 2 Feb. 2019
|  | SB3/D4/T4 | Mention available time for empty parking | Kartik Tiwari | Completed | 3 Feb. 2019
SB3/US5 | parking will be available only for selected areas | SB3/D5/T1 | Designing of GUI | Kartik Tiwari | Completed | 4 Feb. 2019
|  | SB3/D5/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 5 Feb. 2019
|  | SB3/D5/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 6 Feb. 2019
|  | SB3/D5/T4 | Connection with Database to insert the selected areas. | Kartik Tiwari | Completed | 7 Feb. 2019
|  | SB3/D5/T5 | Matching of selected areas to the parkings. | Kartik Tiwari | Completed | 8 Feb. 2019
SB3/US6 | two wheelers will park seperately | SB3/D6/T1 | Designing of GUI | Kartik Tiwari | Completed | 9 Feb. 2019
|  | SB3/D6/T2 | Validating user input at client level. | Kartik Tiwari | Completed | 10 Feb. 2019
|  | SB3/D6/T3 | Validating user input at server level. | Kartik Tiwari | Completed | 11 Feb. 2019
|  | SB3/D6/T4 | Connection with Database to insert parking for two wheelers. | Mahesh Meena | Completed | 12 Feb. 2019
|  | SB3/D6/T5 | arrange vehicles according to their type. | Mahesh Meena | Completed | 13 Feb. 2019
SB3/US7 | three wheelers will park separately | SB3/D7/T1 | Designing of GUI | Mahesh Meena | Completed | 14 Feb. 2019
|  | SB3/D7/T2 | Validating user input at client level. | Mahesh Meena | Completed | 15 Feb. 2019
|  | SB3/D7/T3 | Validating user input at server level. | Mahesh Meena | Completed | 16 Feb. 2019
|  | SB3/D7/T4 | Connection with Database to insert parking for three wheelers. | Mahesh Meena | Completed | 17 Feb. 2019
|  | SB3/D7/T5 | arrange vehicles according to their type. | Mahesh Meena | Completed | 18 Feb. 2019
SB3/US8 | No parking charges will be there | SB3/D8/T1 | Designing of GUI | Mahesh Meena | Completed | 19 Feb. 2019
|  | SB3/D8/T2 | Connection with Database to insert the data. | Mahesh Meena | Completed | 20 Feb. 2019
|  | SB3/D8/T3 | no charges will be applied for parking. | Mahesh Meena | Completed | 21 Feb. 2019

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 30 | 30 | Tasks
2018-10-18 | 25 | 30
2018-10-20 | 20 | 30
2018-10-21 | 15 | 30
2018-10-22 | 10 | 30
2018-10-23 | 0 | 30
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - Smart Parking System
SB4/US1 | provide some driving tips | SB4/D1/T1 | Creating a web page including driving tips. | Aniket Mathur | In progress | 2019-03-01
|  | SB4/D1/T2 | Apply CSS. | Aniket Mathur | In progress | 2019-03-02
|  | SB4/D1/T3 | Apply Designing. | Aniket Mathur | In progress | 2019-03-03
SB4/US2 | put insert queries | SB4/D2/T1 | Designing of GUI | Aniket Mathur | In progress | 2019-03-04
|  | SB4/D2/T2 | Validating user input at client level. | Aniket Mathur | In progress | 2019-03-05
|  | SB4/D2/T3 | Validating user input at server level. | Aniket Mathur | In progress | 2019-03-06
|  | SB4/D2/T4 | Connection with Database to insert the parking records. | Aniket Mathur | In progress | 2019-03-07
SB4/US3 | put update queries | SB4/D3/T1 | Designing of GUI | Aniket Mathur | In progress | 2019-03-08
|  | SB4/D3/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 2019-03-09
|  | SB4/D3/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 2019-03-10
|  | SB4/D3/T4 | Connection with Database to update the parking records. | Kartik Tiwari | In progress | 2019-03-11
SB4/US4 | put select queries | SB4/D4/T1 | Designing of GUI | Kartik Tiwari | In progress | 2019-03-12
|  | SB4/D4/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 2019-03-13
|  | SB4/D4/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 2019-03-14
|  | SB4/D4/T4 | Connection with Database to search the parking records. | Kartik Tiwari | In progress | 2019-03-15
SB4/US5 | put delete queries | SB4/D5/T1 | Designing of GUI | Kartik Tiwari | In progress | 2019-03-16
|  | SB4/D5/T2 | Validating user input at client level. | Kartik Tiwari | In progress | 2019-03-17
|  | SB4/D5/T3 | Validating user input at server level. | Kartik Tiwari | In progress | 2019-03-18
|  | SB4/D5/T4 | Connection with Database to delere the parking records. | Kartik Tiwari | In progress | 2019-03-19
SB4/US6 | Take a backup | SB4/D6/T1 | Designing of GUI | Kartik Tiwari | In progress | 2019-03-20
|  | SB4/D6/T2 | Validating user input at client level. | Mahesh Meena | In progress | 2019-03-21
|  | SB4/D6/T3 | Validating user input at server level. | Mahesh Meena | In progress | 2019-03-22
|  | SB4/D6/T4 | Connection with Database to take a backup of parkings. | Mahesh Meena | In progress | 2019-03-23
SB4/US7 | Delete a backup | SB4/D7/T1 | Designing of GUI | Mahesh Meena | In progress | 2019-03-24
|  | SB4/D7/T2 | Validating user input at client level. | Mahesh Meena | In progress | 2019-03-25
|  | SB4/D7/T3 | Validating user input at server level. | Mahesh Meena | In progress | 2019-03-26
|  | SB4/D7/T4 | Connection with Database to delete an existing backup. | Mahesh Meena | In progress | 2019-03-27
SB4/US8 | Give feedback or suggestions | SB4/D8/T1 | Designing of GUI | Mahesh Meena | In progress | 2019-03-28
|  | SB4/D8/T2 | Validating user input at client level. | Mahesh Meena | In progress | 2019-03-29
|  | SB4/D8/T3 | Validating user input at server level. | Mahesh Meena | In progress | 2019-03-30
|  | SB4/D8/T4 | Connection with Database to insert the user's feedback. | Mahesh Meena | In progress | 2019-03-31
|  | SB4/D8/T5 | Testing the module on localhost & then on server. | Mahesh Meena | In progress | 2019-04-01

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 33 | 33 | Tasks
2019-01-11 | 26 | 33
2019-01-12 | 20 | 33
2019-01-13 | 15 | 33
2019-01-14 | 8 | 33
2019-01-15 | 0 | 33
0
Days